## Sheet1
2026 Devxchange Project Planning/Budget Form
Budget
Project:
Country:
Lead Member:
Project Start Date:
Project End Date:
Budget Year | 2026
FINANCE SECTION
Projected Exchange Rate:_____________________ |  | Budget Amount
Income | Income Details | CDN$ | Local Currency
| Expected Ending Balance of 2025 | 0
| Expected Income Devxchange of 2026 | 66000
Income local
Income Other
Total Income
Expense | Expense Details (By Category)
| Tere Seedling Site | 20000
| Sherowrobit Site | 20000
| Education | 7000
| Water | 7000
| Relief | 12000
| Total Expense | 66000
| Income minus Expense | 0 | 0
ACTIVITY SECTION | List your in the field objectives and activities to execute that
Timeline | Category (from Expense Details Section) | Activity | Start Date | End Date | Cost | Notes
1st Quarter | Tere Seedling Site | Buy Seeds and Secure Location for Nursery Site | 2025-01-01 | 01-15-2025 | 5000
| Sherowrobit Site | Buy Seeds and Secure Location for Nursery Site | 01-16-2025 | 01-30-2025 | 5000
| Education | Identify Schools that need materials | 02-01-2025 | 02-15-2025 | 650
| Water | Complete a land survey for water | 03-01-2025 | 03-15-2025 | 1325
| Relief | monitor area for emergency needs | 03-16-2025 | 03-30-2025 | 0
2nd Quarter | Tere Seedling Site | Prepare Seedling Site | 04-01-2025 | 04-15-2025 | 5000
| Sherowrobit Site | Prepare Seedling Site | 04-16-2025 | 04-30-2025 | 5000
| Education | Purchase School Materials | 05-01-2025 | 05-15-2025 | 5000
| Water | Purchase Well Materials (construction materials, motor and generator) | 05-16-2025 | 05-30-2025 | 4000
| Relief | Purchase Emergency Distribution Kits | 06-01-2025 | 06-30-2025 | 11000
3rd Quarter | Tere Seedling Site | Train Model Farmers | 07-01-2025 | 07-15-2025 | 5000
| Sherowrobit Site | Train Model Farmers | 07-16-2025 | 07-30-2025 | 5000
| Education | Distribute School Materials | 08-01-2025 | 08-30-2025 | 675
| Water | Construction and Training for Maintenance of Well | 09-01-2025 | 09-30-2025 | 1000
| Relief | Distribute If Necessary | 07-01-2025 | 09-30-2025 | 500
4th Quarter | Tere Seedling Site | Distribute Seedlings to farms | 10-01-2025 | 10-15-2025 | 5000
| Sherowrobit Site | Distribute Seedlings to farms | 10-16-2025 | 10-30-2025 | 5000
| Education | Follow up visits of schools | 11-01-2025 | 11-14-2025 | 675
| Water | Follow up to water sites to ensure in working order | 12-01-2025 | 12-15-2025 | 675
| Relief | Distribute If Necessary | 10-01-2025 | 12-31-2025 | 500
FUNDRAISING SECTION
List fundraising plans to achieve this goal amount for the year
| Fundraising Activity | Donation Goal | Start Date | End Date |  |  | Anticipated Fundraising Budget
| Vendor Fair | 300 | 2025-03-25 |  |  |  | 40
| E Campaign | 1500 | 2025-04-25 |  |  |  | 0